## Sample Bid
PLANNED ACTION | QUANTITY | UNIT PRICE | TOTAL
PARKING LOT IMPROVEMENTS
Concrete Curb Repairs: Demo and remove broken concrete curb at 3 locations. Cut and remove exposed tree roots. Off-haul debris. Form new 12" deep and 6" wide concrete curb. Install 2 rows of #3 rebar. Pour, strip and finish concrete curb. | 72 LF | 89.25 | 6426
Cement Treated Base Repairs: Grind and remove existing asphalt in designated area. Off-haul and dispose of debris at recycling facility. Treat existing base material with 5% Cement to a depth of 12". Fine grade and compact existing base material in preparation for asphalt paving. Apply tack oil to vertical edges of existing asphalt. Place and compact 4" of new hot mix asphalt in 2 separate lifts. | 37,255 SF | 5.3 | 197451
4" Asphalt Repairs: Grind and remove asphalt to a depth of 4" in 5 locations. Off-haul debris. Regrade and compact existing base material as required. Apply tack oil to vertical edges of existing asphalt. Place and compact 4" of hot mix asphalt in 2 separate lifts. | 6,205 SF | 4.19 | 25998
2" Asphalt Mill and Pave: Grind existing asphalt to a depth of 2" in 1 designated location. Off-haul debris. Blow, sweep and clean existing asphalt surface. Install reinforced paving fabric (petromat) over entire area. Place and compact 2" of hot mix asphalt in one lift. | 26, 630 SF | 2.56 | 68172
Seal Coat (2 Coats, 2 Move): Clean the entire designated pavement surface using power blowers as required. Seal cracks 1/4" and larger with Duro-Flex hot applied crack filler as per manufacturer's specifications. Treat oil spots with Polyoil sealant (heavy oil stains may reappear). Apply a two-coat application of Western Colloid #327 seal coat emulsion over entire surface. Squeegee first coat and spray the second coat for optimum coverage. This work to be completed in 2 phases on weekends. | 313,930 SF | 0.125 | 39241
Striping: Restripe all existing pavement markings as per present layout. Includes all parking stalls, directional arrows, ADA symbols, and stenciled markings per present layout. | LS | LS | 9319
Fencing: Furnish and install approximately 284 LF of 8' tall slatted chain link fence with 3 strands of barb wire. Includes 1 EA 20' opening slide gate. Includes top and bottom rail. | LS | LS | 17708
ADA IMPROVEMENTS
ADA Concrete Walkway: Saw-cut, demolish, and remove existing concrete walkway. Off-haul debris. Grade as required to meet ADA slope requirements. Form new concrete walkway and set #4 rebar at 18" on center. Install dowels into existing concrete. Pour and finish new 4" concrete. Includes truncated domes where required. | 530 SF | 22.4 | 11872
ADA Asphalt Leveling: Grind and remove asphalt as required for conforms. Apply tack oil to entire area to receive leveling. Place and compact asphalt as required to create ADA Stalls and loading zone to be ADA compliant with no slope greater that 2% in any direction. Includes flares to existing asphalt. | 1,730 SF | 5.92 | 10241
ADA Striping, Signage, & Wheelstops: Paint new ADA pavement markings affected by this work. Furnish and install 6 pre-cast concrete wheel stops and 6 ADA signs on metal posts set in concrete footing. | LS | LS | 3296
TOTAL |  |  | 389724

## MultiYear Spreadsheet
PLANNED ACTION | ESTIMATED COST | MULTIYEAR STRATEGY
|  | YEAR 1 | YEAR 2 | YEAR 3
PARKING LOT IMPROVEMENTS
Concrete Curb Repairs: Demo and remove broken concrete curb at 3 locations. Cut and remove exposed tree roots. Off-haul debris. Form new 12" deep and 6" wide concrete curb. Install 2 rows of #3 rebar. Pour, strip and finish concrete curb. | 6426 | 6426
Cement Treated Base Repairs: Grind and remove existing asphalt in designated area. Off-haul and dispose of debris at recycling facility. Treat existing base material with 5% Cement to a depth of 12". Fine grade and compact existing base material in preparation for asphalt paving. Apply tack oil to vertical edges of existing asphalt. Place and compact 4" of new hot mix asphalt in 2 separate lifts. | 197451 |  | 197451
4" Asphalt Repairs: Grind and remove asphalt to a depth of 4" in 5 locations. Off-haul debris. Regrade and compact existing base material as required. Apply tack oil to vertical edges of existing asphalt. Place and compact 4" of hot mix asphalt in 2 separate lifts. | 25998 | 25998
2" Asphalt Mill and Pave: Grind existing asphalt to a depth of 2" in 1 designated location. Off-haul debris. Blow, sweep and clean existing asphalt surface. Install reinforced paving fabric (petromat) over entire area. Place and compact 2" of hot mix asphalt in one lift. | 68172 | 68172
Seal Coat (2 Coats, 2 Move): Clean the entire designated pavement surface using power blowers as required. Seal cracks 1/4" and larger with Duro-Flex hot applied crack filler as per manufacturer's specifications. Treat oil spots with Polyoil sealant (heavy oil stains may reappear). Apply a two-coat application of Western Colloid #327 seal coat emulsion over entire surface. Squeegee first coat and spray the second coat for optimum coverage. This work to be completed in 2 phases on weekends. | 39241 |  |  | 39241
Striping: Restripe all existing pavement markings as per present layout. Includes all parking stalls, directional arrows, ADA symbols, and stenciled markings per present layout. | 9319 |  |  | 9319
Fencing: Furnish and install approximately 284 LF of 8' tall slatted chain link fence with 3 strands of barb wire. Includes 1 EA 20' opening slide gate. Includes top and bottom rail. | 17708 | 17708
ADA IMPROVEMENTS
ADA Concrete Walkway: Saw-cut, demolish, and remove existing concrete walkway. Off-haul debris. Grade as required to meet ADA slope requirements. Form new concrete walkway and set #4 rebar at 18" on center. Install dowels into existing concrete. Pour and finish new 4" concrete. Includes truncated domes where required. | 11872 | 11872
ADA Asphalt Leveling: Grind and remove asphalt as required for conforms. Apply tack oil to entire area to receive leveling. Place and compact asphalt as required to create ADA Stalls and loading zone to be ADA compliant with no slope greater that 2% in any direction. Includes flares to existing asphalt. | 10241 | 10241
ADA Striping, Signage, & Wheelstops: Paint new ADA pavement markings affected by this work. Furnish and install 6 pre-cast concrete wheel stops and 6 ADA signs on metal posts set in concrete footing. | 3296 | 3296
TOTAL | 389724 | 143713 | 197451 | 48560

## Assessment Checklist
# | STEP | COMMENTS | COMPLETED?
1 | Get ready to do assessment | Create a site map using Google Earth
Select a paving contractor to help with assessment
2 | Complete assessment by walking the property with a contractor | Define general status for paved surfaces
Make notes on site plan to show:
Potholes and failed areas
Walkways, sidewalks, and paths
Broken or failing curbs and gutters requiring concrete repairs
Trip hazards
ADA compliance issues
Tree root damage
Curb painting (red curbs and handicap)
Signage: ADA and special parking
Parking layout issues
Sports courts
Drainage issues
Identify where paved surfaces are showing the impact of:
Garbage truck travel
High traffic flow
Landscaping impact
Tree root damage
3 | Develop estimates for each action | Create a spreadsheet showing each repair action
Show units for each repair (square footage, lineal feet, etc.)

## PASER Rating System
RATING | SURFACE | VISIBLE DISTRESS | GENERAL CONDITION/TREATMENT
10 | Excellent | None | New paved surface not ready for seal coat
8 | Very Good | Few longitudinal cracks (expansion) | Paved 3-5 years earlier requiring seal coat preventative maintenance
|  | All cracks sealed or tight (open 1/4” or less) | Recent seal coat
|  | Very slight or no raveling, surface shows some traffic wear | Little or no maintenance required
|  | No patching or very few patches in excellent condition | First sign of aging; maintain with routine crack filling and seal coat
6 | Fair | Slight raveling (loss of lines) | Show signs of aging, sound structural condition; could extend life with seal coat
|  | Longitudinal cracking (open 1/4” to 1/2” and some spaced less than 10 feet apart) | May require seal coating or nonstructural overlay
|  | First sign of alligator cracking | Up to 10% of surface failed; remove and replace failed area and seal coat entire surface
Occasional patching in good condition
4 | Poor | Surface raveling | Significant aging and first signs of need for strengthening; would benefit from recycling or overlay
|  | Multiple longitudinal and transverse cracking | Needs patching and major overlay or complete recycling
|  | Alligator cracking (over 25% of surface) | 25% of paved surface failed; remove and replace pavement/correct base failure as required and complete overlay/seal coating of remaining paved surface as needed
Slight rutting or deflection (1/2” deep or less)
Patched in fair to poor condition
Occasional potholes
2 | Very Poor / Failed | Severe alligator cracking (over 25% of surface) | Severe deflection; needs reconstruction with extensive base repair
|  | Severe deflection | Alligator cracking with visible sub-grade and water
|  | Extensive patching in poor condition | Failed; may need total reconstruction
Potholes
Visible pumping